## Sheet1
Related User Story | Task Description | Initial Estimate | Amount Remaining After…
|  |  | Week 1 | Week 2 | Week 3 | Week 4
Mighty Vocab
- | Edit Previous Functionality from Sprint 1 | 1 | 1 | 1 | 1 | 1
Study notecards | Studying (server functionality) | 4 | 4 | 4 | 4 | 4
Study notecards | Studying Page (skip card button) | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Study notecards | Studying Page (submit button - that leads to statistics page) | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Study notecards | Studying/Statistics Page (way to identify cards as correct/incorrect) | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
Study notecards | UI for Studying (on wireframe in slack) | 1 | 1 | 1 | 1 | 1
View notecards | UI for Individual Notecard (on wireframe in slack) | 1 | 1 | 1 | 1 | 1
View statistics | UI for Statistics (on wireframe in slack) | 1 | 1 | 1 | 1 | 1
- | Edit Previous Functionality from Sprint 1 | 1.5 | 0 | 0 | 0 | 0
Manage a collection of notecards | Manage Sets (server functionality) | 4 | 4 | 4 | 4 | 4
Manage a collection of notecards | Manage Sets (add card button) | 0.5 | 0 | 0 | 0 | 0
Manage a collection of notecards | Manage Sets (remove card button) | 0.5 | 0 | 0 | 0 | 0
Manage notecards | Individual Notecard (add to set button) | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Manage notecards | Individual Notecard (cancel button) | 0.5 | 0 | 0 | 0 | 0
Manage a collection of notecards | UI for Managing Sets (on wireframe in slack) | 1.5 | 0 | 0 | 0 | 0
Manage notecards | UI for Individual Notecard (on wireframe in slack) | 1.5 | 0 | 0 | 0 | 0
- | Edit Previous Functionality from Sprint 1 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
- | Build Initial Server Setup | 4 | 4 | 4 | 4 | 4
Log in to application | Login (server functionality) | 2 | 2 | 2 | 2 | 2
Log in to application | Login (once logged in, have sets associated to account stored in sets dropdown) | 1 | 1 | 1 | 1 | 1
Study notecards | Sets Page (study button - takes you to studying page) | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Study notecards | Sets Page (study button - takes you to studying page) | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Manage a collection of notecards | Sets Page (add set button - takes you to manage sets page) | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Manage a collection of notecards | UI for Sets Page (on wireframe image in slack) | 1 | 1 | 1 | 1 | 1
| Estimate Totals | 32 | 26 | 26 | 26 | 26